MSci Project: Modelling Innovation Networks and Analysing Innovation Paths

Project Overview:

The project aims to model innovation networks by adapting methodologies similar to those used in citation network modelling.

Drawing on background literature including papers on modelling citation networks, innovation paths, and social science approaches  to constructing innovation networks (amongst other things), this project will follow a scientific process drawing on preexisting literature on innovation models and recent literature in citation network modelling. 

The approach will involve extracting key parameters from sociological theory (learning from literature such as Gilbert and Watts and similar works) to develop a simple innovation model. The current plan is then to apply innovation path analysis to this artificial network, comparing results against paths applied to real innovation network data to explore the results in terms of the model validity and how different types of innovation path analysis methods behave on real and artificial innovation networks.

Project Timeline

Weeks 3-4 (13th-2nd): Project Setup and Literature Review Consolidation

A. Outline project  plan

- Define plan based on the innovation DAGs project proposal

- Establish clear objectives and success criteria

B. Conduct targeted literature review

- Focus on Gilbert & Watts and related innovation modelling literature

Task 1.1. From Watts and G summary intro ensure that our proposed plan addresses “Towards Future Models of Innovation” critiques of current models. Once modern literature reviewed  (e.g. maybe s&v have more modern lit, see if this passes some of the current critiques).

- Create a summary document tracking which models use which approaches and what patterns they reproduce

- Start a bibliography/reference manager

C. Identify core sociological theories and parameters

- Extract some initial theories that can be translated into model parameters

  - (see task 1.1 for start)

- Megin to sketch some reasoning (for later interrogation) for parameter choices based on the lit

- Keep focused on the purpose: finding information to inform the model—don't rabbit hole away from this

How do these parameters link to real innovation networks and innovation paths? Is it worth considering this yet? 

D. Review algorithms for innovation networks

- Keep notes on what each algorithm does differently and why these matter

- Be sure to ask, as this is an entirely new area of literature and there's bound to be questions

E. Set up project infrastructure

- Set up project management tools and version control for code/data

Weeks 5-6 (2nd-16th): Theoretical Framework Development

A. Study and recreate Evans' citation code to create artificial citation network

- Document any questions on Tim’s code and be sure to ask to fully understand

- Is it worth recreating a basic innovation network too?

B. Review differences in this algorithm compared to the innovation ones & summarize them + make way point

- Make explicit decisions about model scope: e.g. what are we defining as an innovation within the code?

C. Sketch out mathematically what my  new model will look like in terms of how the algorithm will work and what desired statistical outputs we should aim to generate

- Is the algorithm based on a well-chosen selection of a minimal number of key parameters? (almost definitely, what other options are there)

- Is it possible to predict based on an outcome seen via statistics about the model if it is behaving as expected?

- Are the statistical tests that we're reviewing telling us something useful? E.g. something comparable with a real network? E.g. A stat to tell us if the algorithm is behaving predictably in some measurable sense and another that can be used for comparison against a real innovation network. (Find such stats in literature as starting point obviously)

- Is it worth considering how these chosen statistics lean toward the route of comparing with Tim's innovation path model or against real networks or should this come later?

- How does this choice impact the success of the project down the line?

- Validate maths and logic with Tim

- Keep simple!

D. Sketch out what my innovation model algorithm will look like

- Is it testable at checkpoints to avoid wasting time down damagingly long wrong avenues?

- Is it overcomplicated?

Week 7 (17th-24th): A basic model

A. Start writing Python to create the simple innovation model with the simple statistic(s) test

- Is it the appropriate level of simple to start?

- Version control (git) will save headaches later

- Keep a separate document explaining model logic in plain language

Weeks 8-10 (24th-7th): Building Manageable Complexity

A. Add to the existing basic code some more basic statistical outputs  (or potentially even network parameters) that allow us to begin to build manageable complexity/ allow for comparison with real networks/ will allow for comparison with an innovation path interaction with a real network

- Is there enough in my preexisting mathematics, checked with Tim, to develop this next level of complexity naturally, or is more research and architecture editing required?

- Don't try to implement every idea from literature (and potentially maths)—prioritize what's essential

- Is it worth considering what data I’ll need to validate against real networks at this stage, or are more rudimentary statistics still required?

- How do these additions relate to project direction and what does the timeline look like?

Week 11 (8th-Holidays): Implementation Iteration

A. Implement new changes

- Have I considered what went well/less well from last code implementation procedure?

- Do I need to re-review literature?

- How is this likely to affect the project timeline? / Is the implementation on track with the project aims?

Holidays/Week 1 (Term 2): Consolidation and Assessment

A. Run multiple simulations to check for consistency in what I think is right

- Add some double-checking statistics that can be added with low time overhead maybe?

B. Tidy up b*llshit, try not to implement any new (non bs tested) ideas

- Consolidation phase—make sure what I have works reliably

- Address the theoretical shortcomings properly in any bottlenecks that in development were ignored and the most sensible thing to do moving forward regarding them. E.g., too much LLM trickery in the code

- Could I survive a viva on what I have?

- Document what's seriously missing and needs to be added in early Term 2

C. Start thinking about what figures/plots tell this part of the story

- How does this inform the next part of the project?

D. Update project plan to address what's needed so far